## Start
|  |  | Project Manager: Ha Khanh Toan |  | Project Name: Web Blog | [14 empty] | Report Date: 20/08/2024
Project Objective: Complete Function of Login, Manage and Authorize Users of the System, Manage Comment, Post, Notification, Follow of Users
Sub-Objectives |  |  |  | Major Tasks |  | Schedule | [9 empty] | Owners and Helpers
l | l | l | 1 | Plan Project |  | l | l | [8 empty] | D | C | A | B
l |  |  | 2 | List functions of system, draw use case diagram, specify use case |  |  | l | l | [7 empty] | D | C | A | B
l |  |  | 3 | List non-functional requirements |  |  |  | l | [7 empty] | D | C | B | A
l |  |  | 4 | Draw a diagram of the components and how they interact. |  |  |  |  | l | [6 empty] | D | C | B | A
l |  |  | 5 | Draw database diagram, describe the structure of the components | [5 empty] | l | l |  |  |  |  | D | C | A | B
| m |  | 6 | Design interface | [6 empty] | m | m
| m |  | 7 | List the classes and functions that have been unit tested | [7 empty] | m | m
|  | m | 8 | Testing system | [9 empty] | m
|  | m | 9 | Istallation instrutions | [10 empty] | m
|  | m | 10 | Usage Instructions
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
|  |  |  | Risks, Qualitatives, Other Metrics | [5 empty] | Green=Adequate, Yellow=Worrisome, Red=Dangerous
|  |  | 1 | Thiết kế gặp lỗi
|  |  | 2 | Thời gian thực hiện không đủ
|  |  | 3 | Không đúng yêu cầu đặt ra
|  |  | 4 | Project không chạy dc
5
[5 empty] | # Internal People assigned to the project: | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0
System Analysis and Design | Interface and functionality development | System Deployment and User Guide |  |  |  | 2024-08-15 | 2024-08-16 | 2024-08-18 | 2024-08-19 | 2024-08-20 | 2024-08-21 | 2024-08-22 | 2024-08-23 | 2024-08-26 | 2024-08-27 | Tuấn | Nhật | Khang | Long | Anh Toàn
Millions
[21 empty] | Labels | Budgeted | Expended
User Management
Role Management
Login Function
[8 empty] | m | l | q | n |  |  |  |  | A | Primary Owner
[7 empty] | Wingdings | m | l | q | n |  |  |  |  | B | Secondary Owner
[16 empty] | C | Tertiary Owner
[16 empty] | D | Posses Owner
Adequate
Worrisome
Dangerous
Summary & Forecast
Sub-Objectives
Report Dates
Costs and Metrics
Major Tasks
and Risks
Note on J60: Microsoft Office User: Đánh vào m ¦ l ¦ q